## PMR
<<CIELITO ZAMORA SENIOR HIGH SCHOOL>> | [9 empty] | Procurement Monitoring Report as of June 30, 2026
[5 empty] | Actual Procurement Activities | [13 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
5020399000 | 1. GRADUATION/RECOGNITION EXPENSE | SCHOOL | No | SMALL VALUE | N/A | 2026-03-05 | N/A | 2024-03-05 | N/A | N/A | N/A | 2026-03-05 | 2026-03-06 | 2026-03-09 | 2026-03-10 | 2026-03-17 | 2026-03-17 | MOOE | 110000 | 110000 |  | 109899 | 109899 |  | N/A | N/A | check RFQ and profile of Suppliers 03/04/2026 | N/A | N/A | N/A | 2026-03-17
5020301002 | 2. Procurement of Test Materials for printing of test Paper to PROCUREMENT SERVICE (PS-available ) | SCHOOL | No | Negotiated procurement | N/A | n/a | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-19 | MOOE | 17442.11 | 17442.11 |  | 17442.11 | 17442.11 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-18 | changes in the mode of procurement from small value to negotiated procurement completed
5020301002 | 3. Office Supplies Expense - ( to Pandayan Bookshopdue to non available ) | SCHOOL | No | small value | N/A | 2026-03-24 | N/A | 2026-03-24 | N/A | N/A | N/A | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-31 | 2026-03-31 | MOOE | 35000 | 35000 |  | 31016.13 | 31016.13 |  | N/A | N/A | check RFQ and profile of Suppliers 03/24/2026 | N/A | N/A | N/A | 2026-03-31 | changes in modes of procurement due to non -availability of stock, from negotiated to small value, completed
5020399000 | 2. Procurement of Test Materials for printing of test Paper to PANDAYAN BOOKSHOPINC (Non-available) | SCHOOL | No | SMALL VALUE | N/A | 2026-03-24 | N/A | 2026-03-24 | N/A | N/A | N/A | 2026-03-25 | 2026-03-25 | 2026-04-06 | 2026-04-08 | 2026-04-14 | 2026-04-14 | MOOE | 42557.89 | 42557.89 |  | 30218.85 | 30218.85 |  | N/A | N/A | check RFQ and profile of Suppliers 03/24/2026 | N/A | N/A | N/A | 2026-04-14 | Completed
5020201002 | 3. GAD SEMINAR- | SCHOOL | No | SMALL VALUE | N/A | 2026-05-19 | N/A | 2026-05-19 | N/A | N/A | N/A | 2026-05-19 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-26 | 2026-05-26 | MOOE | 97600 | 97600 |  | 87170 | 87170 |  | N/A | N/A | 2026-05-18 | N/A | N/A | N/A | 2026-05-26 | Completed
5021304002 | 4. Repair of Roofing & Ceiling in Building I | school | No | small value | N/A | 2026-03-23 | N/A | 2026-03-23 | N/A | N/A | N/A | 2026-03-24 | 2026-03-26 | 2026-04-06 | 2026-04-08 | 2026-05-28 | 2026-05-28 | MOOE | 69804.38 | 69804.38 |  | 65006.16 | 65006.16 |  | N/A | N/A | 2026-03-23 | N/A | N/A | N/A | 2026-05-28 | Completed
5021304002 | 5. Repair/ Rehabilitation of Room 101 & 102 - | school | No | small value | N/A | 2026-03-23 | N/A | 2023-03-23 | N/A | n/a | n/a | 2026-03-24 | 2026-03-26 | 2026-04-06 | 2026-04-08 | 2026-05-28 | 2026-05-28 | MOOE | 179860.93 | 179860.93 |  | 178211.52 | 178211.52 |  | N/A | N/A | 2026-03-23 | N/A | N/A | N/A | 2026-05-28 | Completed
5021304002 | 6. Repair / Rehabilitation of flooring of 2 classroom at Building 2 | school | No | smallvalue | N/A | 2026-04-29 | N/A | 2026-04-29 | n/a | n/a | n/a | 2026-05-05 | 2026-05-07 | 2026-05-19 | 2026-05-21 | 2026-06-29 | 2026-06-29 | MOOE | 229874.32 | 229874.32 |  | 227971.59 | 227971.59 |  | N/A | N/A | 2026-04-29 | N/A | N/A | N/A | 2026-06-29 | Completed
[18 empty] | Total Allotted Budget of Procurement Activities | 782139.63 | 782139.63 | 0
[18 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 746935.36 | 746935.36 | 0
[18 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 35204.27
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
ONGOING PROCUREMENT ACTIVITIES
| Procurement of Fire Extinguisher | school | No | small value | n/a | 2026-06-09 | n/a | 2026-06-09 | n/a | n/a | n/a | 2026-06-22 | 2026-06-22 | 2026-06-29 | 2026-07-10 |  |  | MOOE | 20000 | 20000 |  | 18000 | 18000 |  | N/A | N/A | 2026-06-09 | N/A | N/A | N/A |  | Awarded with issued Notice of Award
[18 empty] | Total Allotted Budget of On-going Procurement Activities | 20000 | 20000 | 0 | 18000 | 18000 | 0
|  | Prepared by: | [7 empty] | Recommended for Approval by: | [11 empty] | APPROVED:
|  | CRISTINA T. BALINGCOS | [7 empty] | ERWIN A. MARIANO | [11 empty] | LYN MARIA M. TARRAYO
|  | BAC SECRETARIAT | [7 empty] | BAC Chairperson/MASTER TEACHER I
Head of the Procuring Entity

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds | Mode of Procurement
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget) | Competitive Bidding
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget) | Limited Source Bidding
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget) | Direct Contracting
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution | Repeat Order
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution | Shopping 52.1(a) - Unforeseen Contingency
Failed under Section 35.1 (b) |  | BAC Resolution |  | Shopping 52.1(b) - Regular Office Supplies and Equipment not available in PS
Failed under Section 35.1 (c) |  | Award |  | Negotiated Procurement - Two Failed Biddings
Failed under Section 41 (b) |  | Cancelled |  | Negotiated Procurement - Emergency Cases
Failed under Section 41 (c) |  |  |  | Negotiated Procurement - Take-Over of Contracts
Contract was extended |  |  |  | Negotiated Procurement - Adjacent or Contiguous
Contract was renewed |  |  |  | Negotiated Procurement - Agency-to-Agency
Cancelled |  |  |  | Negotiated Procurement - Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
Others, please encode directly on the cell |  |  |  | Negotiated Procurement - Highly Technical Consultants
Negotiated Procurement - Defense Cooperation Agreement
Negotiated Procurement - Small Value Procurement
Negotiated Procurement - Lease of Real Property and Venue
Negotiated Procurement - NGO Participation
Negotiated Procurement - Community Participation
Negotiated Procurement - UN Agencies, Int'l Organizations or International Financing Institutions
Negotiated Procurement - Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant Products, Electronic Charging Devices, and Online Subscriptions
Foreign Guidelines - Competitive Bidding
Foreign Guidelines - Alternative Method
Competitive Dialogue
Unsolicited Offer with Bid Matching
Direct Acquisition
Direct Sales
Direct Procurement for Science, Technology, and Innovation
Others, specify in the remarks: Mode of Procurement use <Mode>